## Sheet1
Project: Intake Workspace Server: infopediaproduction.visualstudio.com\infopediaproduction Query: EOW List type: Flat
ID | Work Item Type | Title | State | Urgency | Level of Effort | Tags | Assigned To | Created Date | Closed Date
5451 | Publishing Request | Dynamics Video Tagging (High)(Small) | Closed | 1 - High | 1 - Small | C+E Team; ready to be resolved; v-aakja; v-kandma; v-syasi; v-yenar | Camilla Cooper | 2018-05-31 17:04 | 2018-06-04 08:52
5452 | Task | (1409)Cloud and Enterprise - Publishing Request (update) asset (content/link) (Medium)(Extra Small - 15-30 minutes) - Change request | Closed | 1 - High | 0 - X-Small | ready to be resolved; v-leedav | Jason Gayler | 2018-06-01 07:12 | 2018-06-05 11:15
5453 | Task | (1401)Cloud and Enterprise - Publishing Request (submit newsletter article) ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 1 - Small | ready to be resolved; v-leedav | Jason Gayler | 2018-06-01 07:53 | 2018-06-01 09:55
5454 | Task | (1402)Cloud and Enterprise - Publishing Request (submit newsletter article) ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 1 - Small | ready to be resolved; v-trborr | Jason Gayler | 2018-06-01 07:58 | 2018-06-01 11:53
5456 | Task | (1407)Cloud and Enterprise - Publishing Request (submit newsletter article) ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 1 - Small | ready to be resolved; v-leedav | Jason Gayler | 2018-06-01 08:31 | 2018-06-01 10:08
5457 | Task | (1408)Cloud and Enterprise - Publishing Request (submit newsletter article) ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 1 - Small | ready to be resolved; v-jessto | Jason Gayler | 2018-06-01 08:33 | 2018-06-01 13:44
5459 | Task | (1411)Cloud and Enterprise - Publishing Request (submit newsletter article) ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 1 - Small | ready to be resolved; v-leedav | Jason Gayler | 2018-06-01 08:36 | 2018-06-01 11:54
5460 | Task | (1412)Cloud and Enterprise - Publishing Request (submit newsletter article) ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 1 - Small | ready to be resolved; v-leedav | Jason Gayler | 2018-06-01 08:39 | 2018-06-01 11:55
5461 | Publishing Request | Gather Search Crawl Metrics - June (High)(Med) | Closed | 1 - High | 2 - Medium | v-aakja; v-chpri; v-jessto; v-josham; v-kandma; v-prnee; v-syasi; v-yenar | Maureen Palmer | 2018-06-01 09:21 | 2018-06-08 16:39
5462 | Publishing Request | WWIC: Incentive program card (high)(medium) | Closed | 1 - High | 2 - Medium | crawled; ready to be resolved; v-josham | Ciam Sawyer | 2018-06-01 10:21 | 2018-06-04 11:06
5463 | Publishing Request | Featured Card Update (high)(small) | Closed | 1 - High | 1 - Small | ready to be resolved; v-jessto | Valerie Siu | 2018-06-01 10:21 | 2018-06-01 12:44
5464 | Publishing Request | WWIC: New contest screamer (high)(medium) | Closed | 1 - High | 2 - Medium | crawled; ready to be resolved; v-trborr | Ciam Sawyer | 2018-06-01 10:55 | 2018-06-01 14:35
5465 | Task | (1414)Cloud and Enterprise - Publishing Request (add) content to a page ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 0 - X-Small | ready to be resolved; v-josham | Jason Gayler | 2018-06-01 11:56 | 2018-06-01 15:14
5466 | Task | (1415)Cloud and Enterprise - Publishing Request (add) content to a page ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 0 - X-Small | ready to be resolved; v-trborr | Jason Gayler | 2018-06-01 11:57 | 2018-06-01 13:48
5467 | Publishing Request | Multiple Card Deletion Request (medium)(large) | Closed | 2 - Medium | 3 - Large | offshore; ready to be resolved; v-aakja; v-kandma; v-prnee; v-syasi | John Alsoszatai-Petheo | 2018-06-01 12:18 | 2018-06-05 09:15
5468 | Task | (200)Learning Production Request - Programs - Other (add new content) (-G04) | Closed | 2 - Medium | 1 - Small | ready to be resolved; v-jessto | Jason Gayler | 2018-06-01 12:30 | 2018-06-01 15:15
5469 | Task | (201)Learning Production Request - Programs - Other (add new content) (-G04) | Closed | 2 - Medium | 1 - Small | crawled; ready to be resolved; v-trborr | Jason Gayler | 2018-06-01 12:30 | 2018-06-04 16:42
5458 | Task | (1410)Cloud and Enterprise - Publishing Request (submit newsletter article) (High)(Extra Small - 15-30 minutes) (-G01) | Closed | 1 - High | 1 - Small | v-leedav; waiting for crawl | Jason Gayler | 2018-06-01 08:34 | 2018-06-04 13:26
5471 | Publishing Request | OneHR_Page updates(high)(small) | Closed | 1 - High | 1 - Small | Maintenance; OneHR; ready to be resolved; v-josham | Vyshnave Lalpet Kripakaran | 2018-06-01 13:38 | 2018-06-04 09:47
5473 | Task | (1413)Cloud and Enterprise - Publishing Request (submit newsletter article) ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 1 - Small | v-leedav; waiting for crawl | Jason Gayler | 2018-06-01 13:49 | 2018-06-01 16:20
5474 | Task | (1416)Cloud and Enterprise - Publishing Request (submit newsletter article) ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 1 - Small | v-leedav | Jason Gayler | 2018-06-01 13:51 | 2018-06-04 09:40
5476 | Task | (1417)Cloud and Enterprise - Publishing Request (submit newsletter article) ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 1 - Small | ready to be resolved; v-jessto | Jason Gayler | 2018-06-01 14:09 | 2018-06-01 16:02
5477 | Task | (1418)Cloud and Enterprise - Publishing Request (submit newsletter article) ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 1 - Small | v-leedav; waiting for crawl | Jason Gayler | 2018-06-01 14:09 | 2018-06-01 16:19
5478 | Task | (1419)Cloud and Enterprise - Publishing Request (update) asset (content/link) ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 1 - Small | ready to be resolved; v-leedav | Jason Gayler | 2018-06-01 14:41 | 2018-06-05 11:16
5480 | Task | (1420)Cloud and Enterprise - Publishing Request (submit newsletter article) ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 1 - Small | ready to be resolved; v-trborr | Jason Gayler | 2018-06-01 15:59 | 2018-06-01 20:32
5481 | Task | (1421)Cloud and Enterprise - Publishing Request (submit newsletter article) ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 1 - Small | ready to be resolved; v-trborr | Jason Gayler | 2018-06-01 16:00 | 2018-06-01 20:36
5482 | Publishing Request | CFA_Dewey Targeting_Required_Recommended and Highly Rec courses(high)(small) | Closed | 1 - High | 1 - Small | CFA; dewey; ready to be resolved; targeting; v-jessto | Jason Gayler | 2018-06-01 16:13 | 2018-06-05 12:43
5486 | Task | (1426)Cloud and Enterprise - Publishing Request (update) asset (content/link) ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 1 - Small | ready to be resolved; v-jessto | Jason Gayler | 2018-06-04 07:59 | 2018-06-04 12:56
5487 | Task | (1427)Cloud and Enterprise - Publishing Request (update) asset (content/link) ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 1 - Small | ready to be resolved; v-josham | Jason Gayler | 2018-06-04 08:03 | 2018-06-04 12:32
5489 | Task | (1428)Cloud and Enterprise - Publishing Request (update) asset (content/link) ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 1 - Small | ready to be resolved; v-josham | Jason Gayler | 2018-06-04 08:16 | 2018-06-04 12:35
5490 | Task | (199)Learning Production Request - Programs - Other (update existing content) (-G04) | Closed | 2 - Medium | 1 - Small | ready to be resolved; v-josham | Jason Gayler | 2018-06-04 09:45 | 2018-06-04 12:38
5496 | Publishing Request | CSS Learning_Dynamics_Finance & Operations (med)(med) | Closed | 2 - Medium | 2 - Medium | CSS Learning; ready to be resolved; Search; tagging; v-trborr | Vyshnave Lalpet Kripakaran | 2018-06-04 11:04 | 2018-06-06 10:09
5497 | Task | Reporting Metrics | Active | 2 - Medium | 2 - Medium | v-leedav | Jason Gayler | 2018-06-04 11:40
5498 | Task | (1423)Cloud and Enterprise - Publishing Request (submit newsletter article) (High)(Extra Small - 15-30 minutes) (-G01) | Closed | 1 - High | 1 - Small | crawled; ready to be resolved; v-aakja; v-trborr | Jason Gayler | 2018-06-04 11:55 | 2018-06-06 00:07
5499 | Task | (1424)Cloud and Enterprise - Publishing Request (submit newsletter article) (High)(Extra Small - 15-30 minutes) (-G01) | Closed | 1 - High | 1 - Small | ready to be resolved; v-leedav | Jason Gayler | 2018-06-04 11:55 | 2018-06-05 12:03
5500 | Publishing Request | MS business Operations_Required training targeting(high)(small) | Closed | 1 - High | 1 - Small | dewey; MS Operations; ready to be resolved; required training targeting; v-jessto | Vyshnave Lalpet Kripakaran | 2018-06-04 11:56 | 2018-06-08 15:23
5501 | Task | (1425)Cloud and Enterprise - Publishing Request (submit newsletter article) ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 1 - Small | v-leedav; waiting for crawl | Jason Gayler | 2018-06-04 11:56 | 2018-06-04 13:26
5502 | Task | (1429)Cloud and Enterprise - Publishing Request (submit newsletter article) ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 1 - Small | v-leedav; waiting for crawl | Jason Gayler | 2018-06-04 11:57 | 2018-06-04 13:27
5503 | Task | (1431)Cloud and Enterprise - Publishing Request (update) several assets on my page ()(Extra Small - 15-30 minutes) (-G01) | Closed | 1 - High | 1 - Small | ready to be resolved; v-trborr | Jason Gayler | 2018-06-04 12:00 | 2018-06-05 12:18
5504 | Publishing Request | delete page and cards (medium)(medium) | Closed | 2 - Medium | 2 - Medium | ready to be resolved; v-josham | Ciam Sawyer | 2018-06-04 12:42 | 2018-06-04 13:59
5505 | Publishing Request | card deletion (medium)(small) | Closed | 2 - Medium | 1 - Small | ready to be resolved; v-josham | Ciam Sawyer | 2018-06-04 12:47 | 2018-06-04 13:59
5506 | Task | (1430)Cloud and Enterprise - Publishing Request (add) content to a page ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 0 - X-Small | ready to be resolved; v-josham | Jason Gayler | 2018-06-04 13:32 | 2018-06-04 16:24
5508 | Publishing Request | Add lightbox to tab POC (low)(med) | Closed | 3 - Low | 2 - Medium | v-trborr | Jason Gayler | 2018-06-04 14:38 | 2018-06-05 08:02
5509 | Task | (1433)Cloud and Enterprise - Publishing Request (update) asset (content/link) ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 0 - X-Small | ready to be resolved; v-aakja; v-prnee | Jason Gayler | 2018-06-04 15:49 | 2018-06-04 23:46
5510 | Task | (1434)Cloud and Enterprise - Publishing Request (add) content to a card ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 1 - Small | ready to be resolved; v-trborr | Jason Gayler | 2018-06-05 07:04 | 2018-06-05 11:19
5511 | Task | (1435)Cloud and Enterprise - Publishing Request (update) page ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 1 - Small | crawled; ready to be resolved; v-trborr | Jason Gayler | 2018-06-05 07:05 | 2018-06-05 12:21
5512 | Task | (1436)Cloud and Enterprise - Publishing Request (add) content to a card ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 1 - Small | ready to be resolved; v-leedav | Jason Gayler | 2018-06-05 07:08 | 2018-06-05 13:28
5513 | Task | (1437)Cloud and Enterprise - Publishing Request (add) content to a card ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 1 - Small | ready to be resolved; v-jessto | Jason Gayler | 2018-06-05 07:08 | 2018-06-05 12:25
5514 | Task | (1438)Cloud and Enterprise - Publishing Request (update) asset (content/link) ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 0 - X-Small | ready to be resolved; v-jessto | Jason Gayler | 2018-06-05 08:22 | 2018-06-05 23:11
5515 | Task | (1439)Cloud and Enterprise - Publishing Request (update) asset (content/link) ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 0 - X-Small | ready to be resolved; v-leedav | Jason Gayler | 2018-06-05 08:23 | 2018-06-05 14:42
5516 | Task | (1440)Cloud and Enterprise - Publishing Request (update) asset (content/link) ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 0 - X-Small | crawled; ready to be resolved; v-leedav | Jason Gayler | 2018-06-05 08:23 | 2018-06-06 00:01
5517 | Task | (1441)Cloud and Enterprise - Publishing Request (update) asset (content/link) ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 0 - X-Small | ready to be resolved; v-trborr | Jason Gayler | 2018-06-05 08:23 | 2018-06-05 11:22
5518 | Task | (1442)Cloud and Enterprise - Publishing Request (update) asset (content/link) ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 0 - X-Small | crawled; ready to be resolved; v-trborr | Jason Gayler | 2018-06-05 09:22 | 2018-06-05 13:44
5519 | Task | (1443)Cloud and Enterprise - Publishing Request (do something not listed here) ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 1 - Small | escalated to LOps; ready to be resolved; v-jessto | Jason Gayler | 2018-06-05 09:24 | 2018-06-07 12:58
5520 | Task | (1444)Cloud and Enterprise - Publishing Request (add) content to a page ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 1 - Small | ready to be resolved; v-leedav | Jason Gayler | 2018-06-05 10:24 | 2018-06-05 13:49
5521 | Publishing Request | One Page Cheat Sheet for common terms and defination (High)(Medium) | Active | 1 - High | 2 - Medium | v-jessto; v-josham | Jason Gayler | 2018-06-05 11:36
5522 | Task | (210)Learning Production Request - Programs - Other (add new content) (-G04) | Closed | 2 - Medium | 1 - Small | ready to be resolved; v-trborr | Jason Gayler | 2018-06-05 11:37 | 2018-06-05 16:15
5523 | Task | (211)Learning Production Request - Programs - Other (add new content) (-G04) | Closed | 2 - Medium | 1 - Small | ready to be resolved; v-leedav | Jason Gayler | 2018-06-05 11:37 | 2018-06-05 14:43
5524 | Task | (212)Learning Production Request - Programs - Other (add new content) (-G04) | Closed | 2 - Medium | 1 - Small | ready to be resolved; v-leedav | Jason Gayler | 2018-06-05 11:37 | 2018-06-05 16:38
5526 | Task | (214)Learning Production Request - Programs - Other (add new content) (-G04) | Closed | 2 - Medium | 1 - Small | ready to be resolved; v-jessto | Jason Gayler | 2018-06-05 11:38 | 2018-06-05 16:25
5527 | Task | (215)Learning Production Request - Programs - Other (add new content) (-G04) | Closed | 2 - Medium | 1 - Small | ready to be resolved; v-leedav | Jason Gayler | 2018-06-05 11:38 | 2018-06-05 16:38
5528 | Task | (216)Learning Production Request - Programs - Other (add new content) (-G04) | Closed | 2 - Medium | 1 - Small | ready to be resolved; v-leedav | Jason Gayler | 2018-06-05 11:38 | 2018-06-05 16:40
5530 | Publishing Request | OneHR Page urls_inconsistancy(high)(small) | Closed | 1 - High | 1 - Small | Maintenance; OneHR; ready to be resolved; v-jessto | Vyshnave Lalpet Kripakaran | 2018-06-05 11:40 | 2018-06-06 11:59
5531 | Task | (1445)Cloud and Enterprise - Publishing Request (add) content to a page ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 1 - Small | ready to be resolved; v-trborr | Jason Gayler | 2018-06-05 13:01 | 2018-06-06 09:00
5532 | Task | (1446)Cloud and Enterprise - Publishing Request (update) asset (content/link) ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 0 - X-Small | ready to be resolved; v-trborr | Jason Gayler | 2018-06-05 13:07 | 2018-06-05 16:21
5536 | Publishing Request | Inspire POC 3rd attempt(High)(medium) | Closed | 1 - High | 2 - Medium | offshore; v-aakja; v-chpri; v-josham; work in progress | Joshua Hammack | 2018-06-05 13:22 | 2018-06-06 15:28
5537 | Task | (1447)Cloud and Enterprise - Publishing Request (add) content to a card ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 1 - Small | ready to be resolved; v-aakja; v-prnee | Jason Gayler | 2018-06-05 13:56 | 2018-06-05 23:54
5538 | Publishing Request | G01 - Create Placeholdes for FY19 PST BoM Content (med)(large) | Resolved | 2 - Medium | 3 - Large | ready to be resolved; v-aakja; v-kandma; v-syasi; v-yenar | Caitlin Charles | 2018-06-05 14:21
5539 | Task | (1448)Cloud and Enterprise - Publishing Request (update) asset (content/link) ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 0 - X-Small | ready to be resolved; v-aakja; v-prnee | Jason Gayler | 2018-06-05 15:22 | 2018-06-05 23:56
5540 | Publishing Request | CSS Learning_WDG_Windows commercial page updates(high)(small) | Closed | 1 - High | 1 - Small | CSS Learning; Maintenance; ready to be resolved; v-aakja | Vyshnave Lalpet Kripakaran | 2018-06-05 17:31 | 2018-06-06 10:24
5546 | Task | (1449)Cloud and Enterprise - Publishing Request (submit newsletter article) ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 1 - Small | crawled; ready to be resolved; v-trborr | Jason Gayler | 2018-06-06 10:09 | 2018-06-06 22:53
5547 | Task | (1451)Cloud and Enterprise - Publishing Request (update) asset (content/link) ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 0 - X-Small | crawled; ready to be resolved; v-trborr | Jason Gayler | 2018-06-06 10:18 | 2018-06-06 22:47
5548 | Task | (1452)Cloud and Enterprise - Publishing Request (update) asset (content/link) ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 0 - X-Small | ready to be resolved; v-jessto | Jason Gayler | 2018-06-06 10:39 | 2018-06-06 15:39
5549 | Publishing Request | Delete docs (Med) (Med) | Closed | 2 - Medium | 2 - Medium | ready to be resolved; v-leedav | Maureen Palmer | 2018-06-06 11:55 | 2018-06-07 09:25
5550 | Publishing Request | MS Business Operations_Owner change(high)(med) | Closed | 1 - High | 2 - Medium | crawled; Maintenance; MS Operations; ready to be resolved; v-trborr | Vyshnave Lalpet Kripakaran | 2018-06-06 11:57 | 2018-06-07 08:57
5551 | Publishing Request | POC Request (high)(small) | Closed | 1 - High | 1 - Small | #Education; #Industry; ready to be resolved; v-jessto | John Alsoszatai-Petheo | 2018-06-06 12:03 | 2018-06-06 19:15
5552 | Task | (1454)Cloud and Enterprise - Publishing Request (update) several assets on my page ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 1 - Small | ready to be resolved; v-leedav | Jason Gayler | 2018-06-06 13:29 | 2018-06-06 16:37
5553 | Task | (1455)Cloud and Enterprise - Publishing Request (update) card ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 0 - X-Small | ready to be resolved; v-jessto | Jason Gayler | 2018-06-06 13:31 | 2018-06-06 15:41
5556 | Publishing Request | BizApps News Hub Docsets (High)(Medium) | Closed | 1 - High | 2 - Medium | C+E Team; ready to be resolved.; v-aakja; v-chpri | Camilla Cooper | 2018-06-06 17:10 | 2018-06-07 10:05
5557 | Publishing Request | Changes to Education Industry ETF site (high)(medium) | Closed | 1 - High | 2 - Medium | #Education; #Industry; ready to be resolved; v-trborr | John Alsoszatai-Petheo | 2018-06-06 22:26 | 2018-06-07 10:03
5558 | Task | (1450)Cloud and Enterprise - Publishing Request (add) card to a page ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 1 - Small | crawled; ready to be resolved; v-trborr | Jason Gayler | 2018-06-07 08:27 | 2018-06-07 13:12
5561 | Task | (1457)Cloud and Enterprise - Publishing Request (submit newsletter article) ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 1 - Small | ready to be resolved; v-jessto | Jason Gayler | 2018-06-07 08:40 | 2018-06-07 14:11
5562 | Task | (1458)Cloud and Enterprise - Publishing Request (submit newsletter article) ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 1 - Small | v-leedav; waiting for crawl | Jason Gayler | 2018-06-07 08:43 | 2018-06-07 09:25
5563 | Task | (1459)Cloud and Enterprise - Publishing Request (submit newsletter article) ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 1 - Small | v-leedav; waiting for crawl | Jason Gayler | 2018-06-07 08:47 | 2018-06-07 09:23
5564 | Task | (1460)Cloud and Enterprise - Publishing Request (update) asset (content/link) ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 0 - X-Small | ready to be resolved; v-leedav | Jason Gayler | 2018-06-07 10:18 | 2018-06-07 11:57
5568 | Task | Updating Publisher Training decks (low)(large) | Active | 3 - Low | 3 - Large | v-jessto | Jason Gayler | 2018-06-07 11:05
5569 | Task | (1462)Cloud and Enterprise - Publishing Request (update) card ()(Extra Small - 15-30 minutes) (-G01) | Closed | 2 - Medium | 1 - Small | ready to be resolved; v-trborr | Jason Gayler | 2018-06-07 11:50 | 2018-06-07 13:13
5570 | Publishing Request | Search cleanup_Hide and Delete assets (high)(small) | Closed | 1 - High | 2 - Medium | cleanup; Maintenance; ready to be resolved; Search; v-leedav | Vyshnave Lalpet Kripakaran | 2018-06-07 12:30 | 2018-06-08 13:42
5571 | Publishing Request | Delete content (Med) (Med) | Closed | 2 - Medium | 2 - Medium | ready to be resolved; v-trborr | Maureen Palmer | 2018-06-07 12:56 | 2018-06-08 08:46
5573 | Publishing Request | Featured Card Update (high)(small) | Closed | 1 - High | 1 - Small | crawled; ready to be resolved; v-trborr | Valerie Siu | 2018-06-08 09:13 | 2018-06-08 12:24
5576 | Task | (227)Learning Production Request - Compete - (do batch publishing (>1asset)) (-G04) | Active | 2 - Medium |  | ready to be resolved; v-trborr | Jason Gayler | 2018-06-08 10:46
5577 | Publishing Request | Publish Tech Level Doc (High) (XS) | Closed | 1 - High | 0 - X-Small | crawled; ready to be resolved; v-josham | Maureen Palmer | 2018-06-08 11:24 | 2018-06-08 13:35
5578 | Publishing Request | BizApps submission form updates (High)(Small) | Active | 1 - High | 1 - Small | C+E Team; ready to be resolved; v-trborr | Jason Gayler | 2018-06-08 13:00
5579 | Publishing Request | OHS_MOPR Page Updates(med)(med) | Active | 2 - Medium | 2 - Medium | Maintenance; offshore; OHS; v-leedav | Jason Gayler | 2018-06-08 13:31
5580 | Publishing Request | Add descriptions to HPM site (med)(small) | Active | 2 - Medium | 1 - Small | ready to be resolved; v-leedav | Jason Gayler | 2018-06-08 13:39
5581 | Publishing Request | Remove page from JSON (med)(x-small) | New | 2 - Medium | 0 - X-Small |  | Jean Feil | 2018-06-08 14:38
5582 | Publishing Request | C+E News Hub > Update submission forms (med)(med) | Active | 2 - Medium | 2 - Medium | C+E Team; v-jessto; waiting for stakeholder | Jason Gayler | 2018-06-08 14:43
5583 | Task | Create Queries to sub divide tasks and publishing requests into digestible stats(medium)(medium) | Active | 2 - Medium | 2 - Medium | v-josham | Jason Gayler | 2018-06-08 15:54

## VSTS_ValidationWS_1 (hidden)
value doesn't matter | value doesn't matter | value doesn't matter | value doesn't matter | \ | \ | Active | 0 - Critical | 0 - X-Small | Select User... | Active | 0 - Critical | 0 - X-Small | Active | 0 - Critical | 0 - X-Small | Select User... | Select User... | Active | 0 - Critical | Select User... | Active | 0 - Critical | 0 - X-Small | Select User... | Active | 0 - Critical | 0 - X-Small | Select User... | Active | 0 - Critical | 0 - X-Small | Select User... | Closed | Select User... | Communication Request | Active | 0 - Critical | 0 - X-Small | Select User... | Active | Select User...
readOnlyTestRange_@ | readOnlyTestRange_0 | readOnlyTestRange_M/d/yyyy h:mm AM/PM | readOnlyTestRange_General | all_VSTS_b860e5bd_3dec_40d0_a19b_bcb980dd872b_System.AreaPath | \2017-01-29 - 2017-02-04 | Closed | 1 - High | 1 - Small | Aakash Jain | Closed | 1 - High | 1 - Small | Closed | 1 - High | 1 - Small | Aakash Jain | Aakash Jain | Closed | 1 - High | Aakash Jain | Closed | 1 - High | 1 - Small | Aakash Jain | Closed | 1 - High | 1 - Small | Aakash Jain | Closed | 1 - High | 1 - Small | Aakash Jain | Design | Aakash Jain | Epic | Closed | 1 - High | 1 - Small | Aakash Jain | Closed | Aakash Jain
[5 empty] | \2017-02-05 - 2017-02-11 | New | 2 - Medium | 2 - Medium | Aaron Spencer | New | 2 - Medium | 2 - Medium | New | 2 - Medium | 2 - Medium | Aaron Spencer | Aaron Spencer | New | 2 - Medium | Aaron Spencer | New | 2 - Medium | 2 - Medium | Aaron Spencer | New | 2 - Medium | 2 - Medium | Aaron Spencer | New | 2 - Medium | 2 - Medium | Aaron Spencer | Ready | Aaron Spencer | Feature | New | 2 - Medium | 2 - Medium | Aaron Spencer | New | Aaron Spencer
[5 empty] | \2017-02-12 - 2017-02-18 | On hold | 3 - Low | 3 - Large | Anthony Wilbourne (Allyis Inc) | On hold | 3 - Low | 3 - Large | On hold | 3 - Low | 3 - Large | Anthony Wilbourne (Allyis Inc) | Anthony Wilbourne (Allyis Inc) | On hold | 3 - Low | Anthony Wilbourne (Allyis Inc) | On hold | 3 - Low | 3 - Large | Anthony Wilbourne (Allyis Inc) | On hold | 3 - Low | 3 - Large | Anthony Wilbourne (Allyis Inc) | On hold | 3 - Low | 3 - Large | Anthony Wilbourne (Allyis Inc) | all_VSTS_b860e5bd_3dec_40d0_a19b_bcb980dd872b_Test Case_System.State | Anthony Wilbourne (Allyis Inc) | Publishing Request | On hold | 3 - Low | 3 - Large | Anthony Wilbourne (Allyis Inc) | On hold | Anthony Wilbourne (Allyis Inc)
[5 empty] | \2017-02-19 - 2017-02-25 | Removed | all_VSTS_b860e5bd_3dec_40d0_a19b_bcb980dd872b_Communication Request_CustomProcessTemplate.Urgency | 4 - XL | Beverly Greifendorff | Removed | all_VSTS_b860e5bd_3dec_40d0_a19b_bcb980dd872b_Epic_CustomProcessTemplate.Urgency | 4 - XL | Removed | VSTS_b860e5bd_3dec_40d0_a19b_bcb980dd872b_16-E6-C2-E7-AB-8A-5C-FE-4A-37-14-05-48-DB-49-16-86-9B-E2-F2 | 4 - XL | Beverly Greifendorff | Beverly Greifendorff | Removed | all_VSTS_b860e5bd_3dec_40d0_a19b_bcb980dd872b_Feature_CustomProcessTemplate.Urgency | Beverly Greifendorff | Removed | all_VSTS_b860e5bd_3dec_40d0_a19b_bcb980dd872b_Publishing Request_CustomProcessTemplate.Urgency | 4 - XL | Beverly Greifendorff | Removed | all_VSTS_b860e5bd_3dec_40d0_a19b_bcb980dd872b_Reporting Request_CustomProcessTemplate.Urgency | 4 - XL | Beverly Greifendorff | Removed | all_VSTS_b860e5bd_3dec_40d0_a19b_bcb980dd872b_Task_CustomProcessTemplate.Urgency | 4 - XL | Beverly Greifendorff |  | Beverly Greifendorff | Reporting Request | Removed | all_VSTS_b860e5bd_3dec_40d0_a19b_bcb980dd872b_CustomProcessTemplate.Urgency | 4 - XL | Beverly Greifendorff | Removed | Beverly Greifendorff
[5 empty] | \2017-02-26 - 2017-03-04 | Resolved |  | all_VSTS_b860e5bd_3dec_40d0_a19b_bcb980dd872b_Communication Request_CustomProcessTemplate.LevelofEffort | Bhargavi Rengarajan | Resolved |  | all_VSTS_b860e5bd_3dec_40d0_a19b_bcb980dd872b_Epic_CustomProcessTemplate.LevelofEffort | Resolved |  | VSTS_b860e5bd_3dec_40d0_a19b_bcb980dd872b_55-AA-75-59-C0-6D-2E-5F-4A-EE-B5-52-5F-31-BB-73-6A-95-12-26 | Bhargavi Rengarajan | Bhargavi Rengarajan | Resolved |  | Bhargavi Rengarajan | Resolved |  | all_VSTS_b860e5bd_3dec_40d0_a19b_bcb980dd872b_Publishing Request_CustomProcessTemplate.LevelofEffort | Bhargavi Rengarajan | Resolved |  | all_VSTS_b860e5bd_3dec_40d0_a19b_bcb980dd872b_Reporting Request_CustomProcessTemplate.LevelofEffort | Bhargavi Rengarajan | Resolved |  | all_VSTS_b860e5bd_3dec_40d0_a19b_bcb980dd872b_Task_CustomProcessTemplate.LevelofEffort | Bhargavi Rengarajan |  | Bhargavi Rengarajan | Task | Resolved |  | all_VSTS_b860e5bd_3dec_40d0_a19b_bcb980dd872b_CustomProcessTemplate.LevelofEffort | Bhargavi Rengarajan | Resolved | Bhargavi Rengarajan
[5 empty] | \2017-03-05 - 2017-03-11 | all_VSTS_b860e5bd_3dec_40d0_a19b_bcb980dd872b_Communication Request_System.State |  |  | Bryn Suess | all_VSTS_b860e5bd_3dec_40d0_a19b_bcb980dd872b_Epic_System.State |  |  | VSTS_b860e5bd_3dec_40d0_a19b_bcb980dd872b_34-42-E6-C8-FE-F3-D1-71-1D-60-CE-37-0B-8C-EE-48-1B-60-02-74 |  |  | Bryn Suess | Bryn Suess | all_VSTS_b860e5bd_3dec_40d0_a19b_bcb980dd872b_Feature_System.State |  | Bryn Suess | all_VSTS_b860e5bd_3dec_40d0_a19b_bcb980dd872b_Publishing Request_System.State |  |  | Bryn Suess | all_VSTS_b860e5bd_3dec_40d0_a19b_bcb980dd872b_Reporting Request_System.State |  |  | Bryn Suess | Test Item |  |  | Bryn Suess |  | Bryn Suess | Test Case | Test Item |  |  | Bryn Suess | Test Item | Bryn Suess
[5 empty] | \2017-03-12 - 2017-03-18 |  |  |  | Caitlin Charles | [6 empty] | Caitlin Charles | Caitlin Charles |  |  | Caitlin Charles |  |  |  | Caitlin Charles |  |  |  | Caitlin Charles | all_VSTS_b860e5bd_3dec_40d0_a19b_bcb980dd872b_Task_System.State |  |  | Caitlin Charles |  | Caitlin Charles | all_VSTS_b860e5bd_3dec_40d0_a19b_bcb980dd872b_System.WorkItemType | Design |  |  | Caitlin Charles | VSTS_b860e5bd_3dec_40d0_a19b_bcb980dd872b_DC-B2-FE-2B-F1-49-6B-F6-70-31-F4-E0-DE-DD-BD-FD-6F-DA-30-1B | Caitlin Charles
[5 empty] | \2017-03-19 - 2017-03-25 |  |  |  | Charl Lee-Pearce | [6 empty] | Charl Lee-Pearce | Charl Lee-Pearce |  |  | Camilla Cooper |  |  |  | Camilla Cooper |  |  |  | Camilla Cooper |  |  |  | Camilla Cooper |  | Camilla Cooper |  | Ready |  |  | Charl Lee-Pearce |  | Camilla Cooper
[5 empty] | \2017-03-26 - 2017-04-01 |  |  |  | Chris Hughes | [6 empty] | Chris Hughes | Chris Hughes |  |  | Charl Lee-Pearce |  |  |  | Charl Lee-Pearce |  |  |  | Charl Lee-Pearce |  |  |  | Charl Lee-Pearce |  | Charl Lee-Pearce |  | all_VSTS_b860e5bd_3dec_40d0_a19b_bcb980dd872b_System.State |  |  | Chris Hughes |  | Charl Lee-Pearce
[5 empty] | \2017-04-02 - 2017-04-08 |  |  |  | Christopher Doyle (Allyis Inc) | [6 empty] | Christopher Doyle (Allyis Inc) | Christopher Doyle (Allyis Inc) |  |  | Chris Hughes |  |  |  | Chris Hughes |  |  |  | Chris Hughes |  |  |  | Chris Hughes |  | Chris Hughes |  |  |  |  | Christopher Doyle (Allyis Inc) |  | Chris Hughes
[5 empty] | \2017-04-09 - 2017-04-15 |  |  |  | Ciam Sawyer | [6 empty] | Ciam Sawyer | Ciam Sawyer |  |  | Christopher Doyle (Allyis Inc) |  |  |  | Christopher Doyle (Allyis Inc) |  |  |  | Christopher Doyle (Allyis Inc) |  |  |  | Christopher Doyle (Allyis Inc) |  | Christopher Doyle (Allyis Inc) |  |  |  |  | Ciam Sawyer |  | Christopher Doyle (Allyis Inc)
[5 empty] | \2017-04-16 - 2017-04-22 |  |  |  | Dana Jay | [6 empty] | Dana Jay | Dana Jay |  |  | Ciam Sawyer |  |  |  | Ciam Sawyer |  |  |  | Ciam Sawyer |  |  |  | Ciam Sawyer |  | Ciam Sawyer |  |  |  |  | Dana Jay |  | Ciam Sawyer
[5 empty] | \2017-04-23 - 2017-04-29 |  |  |  | Daniela Harr | [6 empty] | Daniela Harr | Daniela Harr |  |  | Dana Jay |  |  |  | Dana Jay |  |  |  | Dana Jay |  |  |  | Dana Jay |  | Dana Jay |  |  |  |  | Daniela Harr |  | Dana Jay
[5 empty] | \2017-04-30 - 2017-05-06 |  |  |  | Danielle Calubaquib | [6 empty] | Danielle Calubaquib | Danielle Calubaquib |  |  | Daniela Harr |  |  |  | Daniela Harr |  |  |  | Daniela Harr |  |  |  | Daniela Harr |  | Daniela Harr |  |  |  |  | Danielle Calubaquib |  | Daniela Harr
[5 empty] | \2017-05-07 - 2017-05-13 |  |  |  | David Lee (Allyis Inc) | [6 empty] | David Lee (Allyis Inc) | David Lee (Allyis Inc) |  |  | Danielle Calubaquib |  |  |  | Danielle Calubaquib |  |  |  | Danielle Calubaquib |  |  |  | Danielle Calubaquib |  | Danielle Calubaquib |  |  |  |  | David Lee (Allyis Inc) |  | Danielle Calubaquib
[5 empty] | \2017-05-14 - 2017-05-20 |  |  |  | Jacob Block (Allyis Inc) | [6 empty] | Jacob Block (Allyis Inc) | Jacob Block (Allyis Inc) |  |  | David Lee (Allyis Inc) |  |  |  | David Lee (Allyis Inc) |  |  |  | David Lee (Allyis Inc) |  |  |  | David Lee (Allyis Inc) |  | David Lee (Allyis Inc) |  |  |  |  | Jacob Block (Allyis Inc) |  | David Lee (Allyis Inc)
[5 empty] | \2017-05-21 - 2017-05-27 |  |  |  | Jason Gayler | [6 empty] | Jason Gayler | Jason Gayler |  |  | Jacob Block (Allyis Inc) |  |  |  | Jacob Block (Allyis Inc) |  |  |  | Jacob Block (Allyis Inc) |  |  |  | Jacob Block (Allyis Inc) |  | Jacob Block (Allyis Inc) |  |  |  |  | Jason Gayler |  | Jacob Block (Allyis Inc)
[5 empty] | \2017-05-28 - 2017-06-03 |  |  |  | Jean Feil | [6 empty] | Jean Feil | Jean Feil |  |  | Jason Gayler |  |  |  | Jason Gayler |  |  |  | Jason Gayler |  |  |  | Jason Gayler |  | Jason Gayler |  |  |  |  | Jean Feil |  | Jason Gayler
[5 empty] | \2017-06-04 - 2017-06-10 |  |  |  | Jeremy Klein | [6 empty] | Jeremy Klein | Jeremy Klein |  |  | Jean Feil |  |  |  | Jean Feil |  |  |  | Jean Feil |  |  |  | Jean Feil |  | Jean Feil |  |  |  |  | Jeremy Klein |  | Jean Feil
[5 empty] | \2017-06-11 - 2017-06-17 |  |  |  | Jessica Stone | [6 empty] | Jessica Stone | Jessica Stone |  |  | Jeremy Klein |  |  |  | Jeremy Klein |  |  |  | Jeremy Klein |  |  |  | Jeremy Klein |  | Jeremy Klein |  |  |  |  | Jessica Stone |  | Jeremy Klein
[5 empty] | \2017-06-18 - 2017-06-24 |  |  |  | John Alsoszatai-Petheo | [6 empty] | John Alsoszatai-Petheo | John Alsoszatai-Petheo |  |  | Jessica Stone |  |  |  | Jessica Stone |  |  |  | Jessica Stone |  |  |  | Jessica Stone |  | Jessica Stone |  |  |  |  | John Alsoszatai-Petheo |  | Jessica Stone
[5 empty] | \2017-06-25 - 2017-07-01 |  |  |  | Joshua Hammack | [6 empty] | Joshua Hammack | Joshua Hammack |  |  | John Alsoszatai-Petheo |  |  |  | John Alsoszatai-Petheo |  |  |  | John Alsoszatai-Petheo |  |  |  | John Alsoszatai-Petheo |  | John Alsoszatai-Petheo |  |  |  |  | Joshua Hammack |  | John Alsoszatai-Petheo
[5 empty] | \2017-07-02 - 2017-07-08 |  |  |  | Ken Mallit | [6 empty] | Ken Mallit | Ken Mallit |  |  | Joshua Hammack |  |  |  | Joshua Hammack |  |  |  | Joshua Hammack |  |  |  | Joshua Hammack |  | Joshua Hammack |  |  |  |  | Ken Mallit |  | Joshua Hammack
[5 empty] | \2017-07-09 - 2017-07-15 |  |  |  | Manish Kandari (Allyis Inc) | [6 empty] | Manish Kandari (Allyis Inc) | Manish Kandari (Allyis Inc) |  |  | Ken Mallit |  |  |  | Ken Mallit |  |  |  | Ken Mallit |  |  |  | Ken Mallit |  | Ken Mallit |  |  |  |  | Manish Kandari (Allyis Inc) |  | Ken Mallit
[5 empty] | \2017-07-16 - 2017-07-22 |  |  |  | Maureen Palmer | [6 empty] | Maureen Palmer | Maureen Palmer |  |  | Manish Kandari (Allyis Inc) |  |  |  | Manish Kandari (Allyis Inc) |  |  |  | Manish Kandari (Allyis Inc) |  |  |  | Manish Kandari (Allyis Inc) |  | Manish Kandari (Allyis Inc) |  |  |  |  | Maureen Palmer |  | Manish Kandari (Allyis Inc)
[5 empty] | \2017-07-23 - 2017-07-29 |  |  |  | Melissa Tilley | [6 empty] | Melissa Tilley | Melissa Tilley |  |  | Maureen Palmer |  |  |  | Maureen Palmer |  |  |  | Maureen Palmer |  |  |  | Maureen Palmer |  | Maureen Palmer |  |  |  |  | Melissa Tilley |  | Maureen Palmer
[5 empty] | \2017-07-30 - 2017-08-05 |  |  |  | Nancy Anderson | [6 empty] | Nancy Anderson | Nancy Anderson |  |  | Melissa Tilley |  |  |  | Melissa Tilley |  |  |  | Melissa Tilley |  |  |  | Melissa Tilley |  | Melissa Tilley |  |  |  |  | Nancy Anderson |  | Melissa Tilley
[5 empty] | \2017-08-06 - 2017-08-12 |  |  |  | Neha Kumari (Tata Consultancy Services) | [6 empty] | Neha Kumari (Tata Consultancy Services) | Neha Kumari (Tata Consultancy Services) |  |  | Nancy Anderson |  |  |  | Nancy Anderson |  |  |  | Nancy Anderson |  |  |  | Nancy Anderson |  | Nancy Anderson |  |  |  |  | Neha Kumari (Tata Consultancy Services) |  | Nancy Anderson
[5 empty] | \2017-08-13 - 2017-08-19 |  |  |  | Priya Choudhary (Allyis Inc) | [6 empty] | Priya Choudhary (Allyis Inc) | Priya Choudhary (Allyis Inc) |  |  | Neha Kumari (Tata Consultancy Services) |  |  |  | Neha Kumari (Tata Consultancy Services) |  |  |  | Neha Kumari (Tata Consultancy Services) |  |  |  | Neha Kumari (Tata Consultancy Services) |  | Neha Kumari (Tata Consultancy Services) |  |  |  |  | Priya Choudhary (Allyis Inc) |  | Neha Kumari (Tata Consultancy Services)
[5 empty] | \2017-08-20 - 2017-08-26 |  |  |  | Samuel Ragsdale | [6 empty] | Samuel Ragsdale | Samuel Ragsdale |  |  | Priya Choudhary (Allyis Inc) |  |  |  | Priya Choudhary (Allyis Inc) |  |  |  | Priya Choudhary (Allyis Inc) |  |  |  | Priya Choudhary (Allyis Inc) |  | Priya Choudhary (Allyis Inc) |  |  |  |  | Samuel Ragsdale |  | Priya Choudhary (Allyis Inc)
[5 empty] | \2017-08-27 - 2017-09-02 |  |  |  | Sarah Saffer | [6 empty] | Sarah Saffer | Sarah Saffer |  |  | Samuel Ragsdale |  |  |  | Samuel Ragsdale |  |  |  | Samuel Ragsdale |  |  |  | Samuel Ragsdale |  | Samuel Ragsdale |  |  |  |  | Sarah Saffer |  | Samuel Ragsdale
[5 empty] | \2017-09-03 - 2017-09-09 |  |  |  | Sharon Gracias | [6 empty] | Sharon Gracias | Sharon Gracias |  |  | Sarah Saffer |  |  |  | Sarah Saffer |  |  |  | Sarah Saffer |  |  |  | Sarah Saffer |  | Sarah Saffer |  |  |  |  | Sharon Gracias |  | Sarah Saffer
[5 empty] | \2017-09-10 - 2017-09-16 |  |  |  | Surendra Saini | [6 empty] | Surendra Saini | Surendra Saini |  |  | Sharon Gracias |  |  |  | Sharon Gracias |  |  |  | Sharon Gracias |  |  |  | Sharon Gracias |  | Sharon Gracias |  |  |  |  | Surendra Saini |  | Sharon Gracias
[5 empty] | \2017-09-17 - 2017-09-23 |  |  |  | Vincent Konkel | [6 empty] | Vincent Konkel | Vincent Konkel |  |  | Surendra Saini |  |  |  | Surendra Saini |  |  |  | Surendra Saini |  |  |  | Surendra Saini |  | Surendra Saini |  |  |  |  | Vincent Konkel |  | Surendra Saini
[5 empty] | \2017-09-24 - 2017-09-30 |  |  |  | Vyshnave Lalpet Kripakaran | [6 empty] | Vyshnave Lalpet Kripakaran | Vyshnave Lalpet Kripakaran |  |  | Valerie Siu |  |  |  | Valerie Siu |  |  |  | Valerie Siu |  |  |  | Valerie Siu |  | Valerie Siu |  |  |  |  | Vyshnave Lalpet Kripakaran |  | Valerie Siu
[5 empty] | \2017-10-01 - 2017-10-07 |  |  |  | Yedidi Narendra | [6 empty] | Yedidi Narendra | Yedidi Narendra |  |  | Vincent Konkel |  |  |  | Vincent Konkel |  |  |  | Vincent Konkel |  |  |  | Vincent Konkel |  | Vincent Konkel |  |  |  |  | Yedidi Narendra |  | Vincent Konkel
[5 empty] | \2017-10-08 - 2017-10-14 |  |  |  | all_VSTS_b860e5bd_3dec_40d0_a19b_bcb980dd872b_Communication Request_System.AssignedTo | [6 empty] | VSTS_b860e5bd_3dec_40d0_a19b_bcb980dd872b_1D-2A-D5-47-BA-5D-5E-22-E5-C1-60-A8-7F-9B-D3-9C-0D-8E-E2-58 | all_VSTS_b860e5bd_3dec_40d0_a19b_bcb980dd872b_Epic_System.AssignedTo |  |  | Vyshnave Lalpet Kripakaran |  |  |  | Vyshnave Lalpet Kripakaran |  |  |  | Vyshnave Lalpet Kripakaran |  |  |  | Vyshnave Lalpet Kripakaran |  | Vyshnave Lalpet Kripakaran |  |  |  |  | Camilla Cooper |  | Vyshnave Lalpet Kripakaran
[5 empty] | \2017-10-15 - 2017-10-21 | [14 empty] | Yedidi Narendra |  |  |  | Yedidi Narendra |  |  |  | Yedidi Narendra |  |  |  | Yedidi Narendra |  | Yedidi Narendra |  |  |  |  | Valerie Siu |  | Yedidi Narendra
[5 empty] | \2017-10-22 - 2017-10-28 | [14 empty] | all_VSTS_b860e5bd_3dec_40d0_a19b_bcb980dd872b_Feature_System.AssignedTo |  |  |  | all_VSTS_b860e5bd_3dec_40d0_a19b_bcb980dd872b_Publishing Request_System.AssignedTo |  |  |  | all_VSTS_b860e5bd_3dec_40d0_a19b_bcb980dd872b_Reporting Request_System.AssignedTo |  |  |  | all_VSTS_b860e5bd_3dec_40d0_a19b_bcb980dd872b_Task_System.AssignedTo |  | all_VSTS_b860e5bd_3dec_40d0_a19b_bcb980dd872b_Test Case_System.AssignedTo |  |  |  |  | all_VSTS_b860e5bd_3dec_40d0_a19b_bcb980dd872b_System.AssignedTo |  | VSTS_b860e5bd_3dec_40d0_a19b_bcb980dd872b_9B-A3-29-D8-40-9B-C9-EE-AE-30-EA-8B-B9-A5-23-26-18-00-CD-7D
\2017-10-29 - 2017-11-04
\2017-11-05 - 2017-11-11
\2017-11-12 - 2017-11-18
\2017-11-19 - 2017-11-25
\2017-11-26 - 2017-12-02
\2017-12-03 - 2017-12-09
\2017-12-10 - 2017-12-16
\2017-12-17 - 2017-12-23
\2017-12-24 - 2017-12-30
\2017-12-31 - 2018-01-06
\2018-01-07 - 2018-01-13
\2018-01-14 - 2018-01-20
\2018-01-21 - 2018-01-27
\2018-01-28 - 2018-02-03
\2018-02-04 - 2018-02-10
\2018-02-11 - 2018-02-17
\2018-02-18 - 2018-02-24
\2018-02-25 - 2018-03-03
\FY18Q4
all_VSTS_b860e5bd_3dec_40d0_a19b_bcb980dd872b_System.IterationPath